Project Erasmus + Cooperation for innovation and exchange of good practice

KA229 - School Exchange Partnerships

The project title: I am my life hero

Students' age: up to 15

Time: September 2018- August 2020

Partners: Poland, Cyprus, Spain, Italy

| no | Event | Mobilities Teachers/Students | Country | Date |
| --- | --- | --- | --- | --- |
| 1 | National Hero Week | no | all | November 2018 |
| 2 | Health Hero Week | 2/3+5/6 | Cyprus | March 2019 |
| 3 | Sport Hero Week | 2/3+5/6 | Italy | May 2019 |
| 4 | Team Hero | 2/3+5/6 | Spain | February 2020 |
| 5 | Final SMART hero Week - to sum up the project | 2/3+5/6 | Poland | May 2020 |

| Date | Ist year 2018/2019 Activity- subjects and tasks | Participants | Methods |
| --- | --- | --- | --- |
| September 2018 | The start of the project-Logo and aims of Erasmus+ presentation of the project- project's aims, countries, map+distances The start of the eTwinning project - to choose the school logo- sts make A3 posters to present the project theme - to work over the word HERO- to describe a hero in adjectives - to prepare a common survey and do it in the schools and communites, The survey about Hero in my life: Have I met any?/ Have I got one?/ Have I ever been? - to sum up the survey according to the age: the olds /adults/ the young/ children and present it in powerpoints - to invite and inform the kindergartens and the minorities about planned events | School coordinatorsAll students 10-15 year- olds 12-year-olds 12-year-olds 11-year-olds | Art and craft brain storming ICT |
| October | Who is Hero: - to make presentations of the schools and countries and inform the communities about the project - to present surveys about Hero - to show presentations of the project and schools on the local level | All students 12-15year-olds | brain storming, mind maps |
| November | 1st Week- National Hero – the school event - to present the hero (whom I admire) of history/ sport/ -poems/ stories/ powerpoints/ art works/ - the leaflet about heros, national holidays concerning the history - a vote for my hero on the website - to visit the place concernig the country hero - to celebrate the hero day at school with the presence of the minorities (kindergartens/the blinds/the olds/the handicaped) | all partners the whole community minorities teachers parents | Art & craft TIK Vote for historical visit |

| January 2019 December | Hero around us- Hero of my relatives - to present good habits- discussion with parents and others, choosing the person - TV spot- a film about my hero - competitions about family hero- posters/photos - presentation of the work at parents' meetings | Families kindergartens 13-15-year-olds all students teachers | Discussion TIK art |
| --- | --- | --- | --- |
| February | I've got the power - How to fight for oneself - interviews, meetings with the blind/ the handicapped/ the minorities - meetings with psychologists , the blind/ handicaped inspiring students – education of motivation- my good features - to prepare drama presentation- role - play - create workshops of talents | Parents kindergartens the minorities | Trip drama Art ICT |
| March | 1st meeting - Healthy Hero in Cyprus - to organise workshops about healthy food & cooking -workshops to cook different recipes with healthy ingredients; alternative healthy cooking vs traditional cooking. - to write the Decalogue of healthy life- posters - construct a food pyramid embodying the Mediterranean nutrition. - design healthy meals according to «My Plate» guidelines. - workshops informing students of all the negatives related to smoking, alcohol, drug and internet addiction. - healthy day " Skip for the heart" - meetings for parents- How to grow up a hero - present the visit meeting in the local newspaper/ website - page of the project diary- memories after the visit | Partners all students groups parents | Event 1st trip art craft ICT workshop |
| April | Hero of active life - to present the 1st visit meeting in the local newspaper/ website - to prepare the next visit- Sports Hero - interviews with sportsmen (old,handicapped,young)- powerpoints, photos, posters | School community kindergartens teachers | Workshops ICT |
| May | 2nd meeting Sport Hero Week in Italy -to organise sports family event- short walks, jogging, school competitions - to present local sports people - page of the project diary- memories after the visit | Partners coordinators | Event 2nd trip ICT |
| June | - Hero Kid- I've got the talent- talent show - exchibition of the project works in front of the school and presentation in the local website/ newspaper - What's the most important in my everyday life? - to continue the blog- 6th page | 12-year- olds teachers | Events ICT |
| July-August 2019 | Holiday competitions: - Photos & short films of heroes - Heroes of the literature- the description of a favourite character - to create quiz Googlemaps - preparation for the project 2nd year | Students 9-12-year-olds teachers | Art writings ICT |

| Date | 2nd year 2019/2020 Activity- subjects and tasks | Participants | Methods |
| --- | --- | --- | --- |
| September | - presentation of holiday competitions - presentation of emaps - the start of eTwinning+ 2nd year | Schools kinderkartens all | Show meetings |
| October | Small and big hands give help - to present the work of local service- policeman, firefighter, doctor - interviews - to practice first aid help- how to help in everyday accidents - presentations/films - to present local authorities- meetings, interviews - to visit places of local workshop- meeting interesting people | 11-12-year-olds local people | Workshops meetings |
| November December | I fight my weak points- I work on my good points - to promote good styles of families- active, healthy - to show healthy recipes of local meals- book of recipes - to present ways of preparing food | All schools kindergartens invited groups | Cooking event Art |
| Februarz January2018 | Our talents - school workshops- the choice of future job- presentation of professions - to exchange talents- meetings with parents, grandparents, others to share | 12-15-year-olds | Meetings event interviews |
| March | 3rd visit Team Hero in Spain - workshop about human towers and benefits of team - Kahoot and other apps for teamwork - meeting with an expert who works cooperatively. - visit buildings built cooperatively in Barcelona. - families introduce jobs where they work in team - visit local radio and visit places where minorities work recycling collaboratively - page of the project diary- memories after the visit | Partners 12-year-olds | 3rd Trip visit |
| April | - to present the 3rd visit meeting in the school/ local newspaper/ website - Technology Week - workshops - invite the minorities into Ozobots- programming, coding - to prepare the next visit- modern technology in education | Local community up to 15-year-olds | ICT Art Craft |
| May | 4th visit Final Week Smart Hero - to sum up the project at the Hero Festival + hero prizes - to present & exchange the calendars of all project works and songs I am the hero - to present the project eTwinning/ blog - page of the project diary- memories after the visit | Partners School community local authorities | Event Art book ICT music |
| June | Presentation of the project at the school community & on the school website - the project book and diary- e-book & printed | All schools | Meetin presentation ICT |
| July | Presentation of the project in the town & the town website | All partners |  |
| August | Presentation of the project in the country final page of the project blog - on the eTwinning site, Erasmus+ | Poland |  |

Final products of the project:

1. school:

- events- meetings, workshops, competitions, discussions, interviews, websites, diary pages of the visits

- emap Google

- diary after the events- ebook, printed

- the project calendar

- the project song I am the hero

- Tutorial National Hero

- Healthy Hero guide

2. local – leaflets, newspaper, websites

3. European- school websites, FBeTwinning project